## Defect Tracking Log
Project Name: CyberRamge
Defect ID | Defect Description | Created On | Created By | Severity | Priority | Status | Assigned Date | Assigned To | Resolution | Resolution Date | Estimated Time To Fix | Actual Time To Fix | Root Cause
CybRng-BUG-001 | Users were able to register multiple accounts using the same email address, causing potential data inconsistency and security concerns. The register method did not check for existing emails before creating new users. | 2025-12-29 | Mohamed Wael | Medium | High | Fixed | 2025-12-29 | Mohamed Wael | Fixed | 2025-12-29 | 8 hours | 9 hours | The register method did not check for existing emails before creating new users.
CybRng-BUG-002 | When a user completed a scenario and returned later, the page automatically redirected to the simulation phase instead of the learning phase, bypassing educational content. The useEffect hook in frontend/app/scenarios/[id]/page.tsx set the phase to simulation when state.simulationUnlocked was true. | 2025-12-29 | Mohamed Wael | Low | High | Fixed | 2025-12-29 | Mohamed Wael | Fixed | 2025-12-29 | 4 hours | 5 hours | The useEffect hook in frontend/app/scenarios/[id]/page.tsx set the phase to simulation when state.simulationUnlocked was true.
CybRng-BUG-003 | Clicking navigation tabs or "Continue" buttons sometimes displayed blank content because the underlying step index did not match the active phase; components attempted to render steps from the wrong phase. | 2025-12-29 | Mohamed Wael | Medium | Medium | Fixed | 2025-12-29 | Mohamed Wael | Fixed | 2025-12-29 | 6 hours | 7 hours | The underlying step index did not match the active phase; components attempted to render steps from the wrong phase.
CybRng-BUG-004 | Accessing "Retake Questionnaire" from the simulation phase caused an immediate crash with TypeError: Cannot read properties of undefined (reading 'questionText'). The handler hardcoded a step index of 0 while switching to the questionnaire phase; step 0 was a learning step so the questionnaire component received no questions. | 2025-12-29 | Mohamed Wael | High | High | Fixed | 2025-12-29 | Mohamed Wael | Fixed | 2025-12-29 | 12 hours | 14 hours | The handler hardcoded a step index of 0 while switching to the questionnaire phase; step 0 was a learning step so the questionnaire component received no questions.
CybRng-BUG-005 | Platform allowed weak passwords (minimum 6 simple characters), not meeting security best practices. Password complexity was missing from both frontend and backend validation. | 2025-12-29 | Mohamed Wael | Medium | High | Fixed | 2025-12-29 | Mohamed Wael | Fixed | 2025-12-29 | 8 hours | 9 hours | Password complexity was missing from both frontend and backend validation.
CybRng-BUG-006 | Retaking the questionnaire to improve a score would reset the user's progress in the backend, locking the simulation again even if the user had already passed. This was destructive to user progress. | 2025-12-29 | Mohamed Wael | Low | High | Fixed | 2025-12-29 | Mohamed Wael | Fixed | 2025-12-29 | 4 hours | 5 hours | Retaking the questionnaire would reset the user's progress in the backend.
CybRng-BUG-007 | Users could access protected routes (/dashboard, /scenarios, /scenarios/[id]) without authentication by entering the URL directly. Protected pages lacked client-side authentication checks and redirects; server-rendered pages did not verify authentication state. | Prior to 2025-12-29 | Mohamed Wael | Critical | High | Fixed | Prior to 2025-12-29 | Mohamed Wael | Fixed | Prior to 2025-12-29 | 16 hours | 18 hours | Protected pages lacked client-side authentication checks and redirects; server-rendered pages did not verify authentication state.
CybRng-BUG-008 | Accessing /admin while not logged in incorrectly redirected users to the student dashboard (/dashboard) instead of the login page. Redirection logic only checked isAuthenticated() by token presence and defaulted incorrectly when a stale token existed but user object was missing. | 2025-12-30 | Mohamed Wael | Low | Medium | Fixed | 2025-12-30 | Mohamed Wael | Fixed | 2025-12-30 | 4 hours | 5 hours | Redirection logic only checked isAuthenticated() by token presence and defaulted incorrectly when a stale token existed but user object was missing.
CybRng-BUG-009 | Expanding a user row in the Admin Dashboard's User Management tab showed "N/A" for the "Joined Date" because the backend UserSchema did not enable timestamps, so createdAt was missing. | 2025-12-30 | Mohamed Wael | Low | Low | Fixed | 2025-12-30 | Mohamed Wael | Fixed | 2025-12-30 | 3 hours | 4 hours | The backend UserSchema did not enable timestamps, so createdAt was missing.
CybRng-BUG-010 | Authenticated users were automatically redirected from the landing page (/) to /dashboard, preventing viewing of landing page content. A useEffect hook in frontend/app/page.tsx called router.replace('/dashboard') on mount. | 2026-01-03 | Mohamed Wael | Low | Medium | Fixed | 2026-01-03 | Mohamed Wael | Fixed | 2026-01-03 | 4 hours | 5 hours | A useEffect hook in frontend/app/page.tsx called router.replace('/dashboard') on mount.
CybRng-BUG-011 | Administrators could manually access the student dashboard (/dashboard) showing student interface with admin data. frontend/app/dashboard/page.tsx lacked role-based redirect guards. | 2026-01-03 | Mohamed Wael | Low | High | Fixed | 2026-01-03 | Mohamed Wael | Fixed | 2026-01-03 | 6 hours | 7 hours | frontend/app/dashboard/page.tsx lacked role-based redirect guards.
CybRng-BUG-012 | Users were being logged out when attempting to access unauthorized routes (e.g., a student accessing /admin). The authentication guard logic redirected to login if the user object had not finished hydrating even when a valid token existed, causing session loss. | 2026-01-03 | Mohamed Wael | Medium | Medium | Fixed | 2026-01-03 | Mohamed Wael | Fixed | 2026-01-03 | 8 hours | 9 hours | The authentication guard logic redirected to login if the user object had not finished hydrating even when a valid token existed.
CybRng-BUG-013 | The user profile update form allowed saving with empty username or email fields. Client-side validation was missing before calling the update API. | 2026-01-03 | Ayad Zewail | Low | High | Fixed | 2026-01-03 | Ayad Zewail | Fixed | 2026-01-03 | 4 hours | 5 hours | Client-side validation was missing before calling the update API.
CybRng-BUG-014 | Signup process only checked for unique emails, allowing multiple accounts with the same username. auth.service.ts lacked a database check for username uniqueness during registration. | 2026-01-03 | Mohamed Wael | Medium | High | Fixed | 2026-01-03 | Mohamed Wael | Fixed | 2026-01-03 | 6 hours | 7 hours | auth.service.ts lacked a database check for username uniqueness during registration.
Note on G4: Raj: Choose from the dropdown list
Note on H4: Raj: Choose from the dropdown list